## Start Here
PROJECT PLAN TEMPLATES
Choose a worksheet that matches your project, then replace the sample tasks with your own.
Included templates | Best for
Simple Project Plan | Small projects with clear tasks, owners, dates, and status
Agile Sprint Plan | Short development sprints, backlog items, and sprint goals
Marketing Campaign | Campaign planning across content, channels, launch, and reporting
Event Plan | Event preparation, vendors, promotion, delivery, and follow-up
Software Implementation | SaaS rollout, configuration, testing, training, and go-live
Blank Project Plan | Copy-ready blank structure for any project
Tip | Use ISO-style dates (YYYY-MM-DD), assign one accountable owner per task, and update status in team check-ins.
Note | Sample tasks and dates are illustrative. Adjust dependencies, dates, and milestones to your project.

## Simple Project Plan
SIMPLE PROJECT PLAN
Replace the sample values. Duration calculates from Start Date and Due Date.
ID | Task / Deliverable | Owner | Start Date | Due Date | Duration (days) | Dependency | Priority | Status | Milestone? | Notes
1 | Confirm scope and success criteria | Project lead | 2026-10-12 | 2026-10-13 |  |  | High | Not started | Yes | Agree what is in and out of scope
2 | Create task list and assign owners | Project lead | 2026-10-14 | 2026-10-15 |  | 1 | High | Not started | No
3 | Complete core work | Workstream owner | 2026-10-16 | 2026-10-23 |  | 2 | High | Not started | No
4 | Review deliverables | Reviewer | 2026-10-26 | 2026-10-27 |  | 3 | Medium | Not started | No
5 | Get approval and close project | Sponsor | 2026-10-28 | 2026-10-29 |  | 4 | High | Not started | Yes | Record lessons learned

## Agile Sprint Plan
AGILE SPRINT PLAN
Replace the sample values. Duration calculates from Start Date and Due Date.
ID | Task / Deliverable | Owner | Start Date | Due Date | Duration (days) | Dependency | Priority | Status | Milestone? | Notes
1 | Agree sprint goal | Product owner | 2026-10-12 | 2026-10-12 |  |  | High | Not started | Yes | Keep the goal outcome-focused
2 | Refine and estimate backlog | Product + team | 2026-10-12 | 2026-10-13 |  | 1 | High | Not started | No
3 | Build sprint stories | Engineering | 2026-10-14 | 2026-10-21 |  | 2 | High | Not started | No
4 | Test and fix defects | QA + engineering | 2026-10-20 | 2026-10-22 |  | 3 | High | Not started | No
5 | Sprint review and retrospective | Scrum team | 2026-10-23 | 2026-10-23 |  | 4 | Medium | Not started | Yes | Capture follow-up actions

## Marketing Campaign
MARKETING CAMPAIGN
Replace the sample values. Duration calculates from Start Date and Due Date.
ID | Task / Deliverable | Owner | Start Date | Due Date | Duration (days) | Dependency | Priority | Status | Milestone? | Notes
1 | Set campaign goal and audience | Marketing lead | 2026-10-12 | 2026-10-13 |  |  | High | Not started | Yes | Define primary KPI
2 | Draft message and creative brief | Content lead | 2026-10-14 | 2026-10-16 |  | 1 | High | Not started | No
3 | Create landing page and assets | Design + web | 2026-10-19 | 2026-10-23 |  | 2 | High | Not started | No
4 | QA links, tracking, and approvals | Marketing ops | 2026-10-26 | 2026-10-27 |  | 3 | High | Not started | No
5 | Launch campaign | Campaign owner | 2026-10-28 | 2026-10-28 |  | 4 | High | Not started | Yes
6 | Review performance and report | Marketing analyst | 2026-11-04 | 2026-11-06 |  | 5 | Medium | Not started | No | Compare results with baseline

## Event Plan
EVENT PLAN
Replace the sample values. Duration calculates from Start Date and Due Date.
ID | Task / Deliverable | Owner | Start Date | Due Date | Duration (days) | Dependency | Priority | Status | Milestone? | Notes
1 | Confirm event objective, date, and budget | Event lead | 2026-10-12 | 2026-10-14 |  |  | High | Not started | Yes
2 | Book venue and key suppliers | Operations | 2026-10-15 | 2026-10-20 |  | 1 | High | Not started | No
3 | Publish registration and promotion | Marketing | 2026-10-21 | 2026-10-28 |  | 1 | High | Not started | No
4 | Confirm agenda, speakers, and run sheet | Program lead | 2026-10-29 | 2026-11-05 |  | 2 | High | Not started | No
5 | Run event | Event team | 2026-11-12 | 2026-11-12 |  | 2,3,4 | High | Not started | Yes
6 | Send follow-up and evaluate results | Event lead | 2026-11-13 | 2026-11-18 |  | 5 | Medium | Not started | No

## Software Implementation
SOFTWARE IMPLEMENTATION
Replace the sample values. Duration calculates from Start Date and Due Date.
ID | Task / Deliverable | Owner | Start Date | Due Date | Duration (days) | Dependency | Priority | Status | Milestone? | Notes
1 | Kickoff and confirm requirements | Implementation lead | 2026-10-12 | 2026-10-15 |  |  | High | Not started | Yes
2 | Configure workspace and permissions | Admin | 2026-10-16 | 2026-10-21 |  | 1 | High | Not started | No
3 | Migrate or import data | Data owner | 2026-10-22 | 2026-10-27 |  | 2 | High | Not started | No | Validate a sample first
4 | User acceptance testing | Business users | 2026-10-28 | 2026-11-03 |  | 3 | High | Not started | No | Log issues and owners
5 | Train users and prepare support | Enablement lead | 2026-11-04 | 2026-11-06 |  | 4 | Medium | Not started | No
6 | Go-live and monitor adoption | Project sponsor | 2026-11-09 | 2026-11-13 |  | 5 | High | Not started | Yes