## Start Here
PROJECT STATUS REPORT TEMPLATES
Use a consistent reporting date and write concise, evidence-based updates. Replace all sample data before sharing.
Worksheet | Use it for
Weekly Status | Team-level weekly update with progress, next steps, risks, decisions, schedule, and budget
Executive Summary | Short leadership view of project health and decisions needed
Risk and Issue Log | Track active risks, issues, owners, responses, and due dates
Milestones | Report planned dates, forecast dates, variance, and completion
Blank Status Report | Copy-ready blank report to customize
RAG status guide | Green = on track; Amber = at risk and needs attention; Red = off track or blocked. Define thresholds for your organization.

## Weekly Status
WEEKLY STATUS
Example data is fictional. Update the report date, health indicators, and actions before sharing.
Field | Example / entry
Project name | Website redesign
Report owner | Project manager
Reporting period | Week ending 2026-10-16
Overall health | Amber
Executive summary | Core page build is progressing. Content approvals are three days late and may affect QA. Sponsor decision on scope is needed by Friday.
Progress this period | Homepage and navigation approved; CMS configuration completed; 6 of 10 priority pages drafted.
Planned next period | Finish remaining copy; complete mobile QA; confirm analytics events.
Schedule health | Amber
Budget health | Green
Scope health | Green
Key decision needed | Approve whether two optional landing pages move to phase two.
Decision owner | Project sponsor
Decision due | 2026-10-16
Next report date | 2026-10-23

## Executive Summary
EXECUTIVE SUMMARY
One-page leadership summary. Keep detail focused on decisions, impact, and forecast.
Section | Update | Health | Owner / decision maker | Due date
Overall status | Amber: content approval is delaying QA. | Amber | Project manager | 2026-10-16
Progress against plan | Core site structure complete; priority content is 60% approved. | Green | Content lead | 2026-10-20
Schedule | Forecast launch may slip by 3 days if copy approval misses deadline. | Amber | Project sponsor | 2026-10-16
Budget | Spend is within approved budget; no change request submitted. | Green | Finance owner | 2026-10-23
Scope | Two optional landing pages may move to phase two. | Amber | Project sponsor | 2026-10-16
Top risk / issue | Late content approval reduces time available for QA. | Red | Content lead | 2026-10-16
Decision requested | Confirm phase-one scope and approve any deferred pages. | Amber | Project sponsor | 2026-10-16
Next milestone | Complete acceptance testing. | Green | QA lead | 2026-10-27

## Risk and Issue Log
RISK AND ISSUE LOG
Distinguish a risk (might happen) from an issue (has happened). Assign an owner and response.
ID | Type | Risk / issue | Impact | Likelihood | Severity | Response / next action | Owner | Due date | Status
R-01 | Risk | Content approval arrives late | Could delay QA and launch | Medium | High | Set approval deadline; escalate unresolved copy | Content lead | 2026-10-16 | Open
I-01 | Issue | Two analytics events fail in staging | Conversion reporting incomplete | High | Medium | Fix event mapping and retest | Analytics lead | 2026-10-20 | In progress
R-02 | Risk | Key developer becomes unavailable | Build tasks may slip | Low | Medium | Document handover and backup coverage | Technical lead | 2026-10-19 | Open

## Milestones
MILESTONES
Compare baseline and current forecast. Variance is forecast date minus planned date.
Milestone | Owner | Planned date | Forecast / actual date | Variance (days) | Status | Notes
Scope approval | Sponsor | 2026-10-12 | 2026-10-12 |  | Complete
Content approval | Content lead | 2026-10-16 | 2026-10-19 |  | At risk | Waiting for final copy review
QA complete | QA lead | 2026-10-27 | 2026-10-30 |  | At risk | Forecast assumes content approved
Launch | Project manager | 2026-10-30 | 2026-11-02 |  | At risk | Confirm after QA

## Blank Status Report
BLANK STATUS REPORT
Copy this worksheet for each reporting period, then replace bracketed prompts.
Section | Your update
Project name | [Enter project name]
Project manager / report owner | [Name]
Reporting period / as-of date | [Date range and status date]
Overall health (Green / Amber / Red) | [Status and one-sentence reason]
Executive summary | [What changed, what matters, and forecast]
Completed this period | [Key deliverables and milestones]
Planned next period | [Top priorities, owners, and due dates]
Schedule health | [On track / at risk / off track plus explanation]
Budget health | [Actual vs budget and forecast, if applicable]
Scope / quality health | [Changes, defects, acceptance concerns]
Top risks and issues | [Impact, response, owner, due date]
Dependencies / blockers | [What is needed, from whom, by when]
Decisions required | [Decision, decision owner, deadline]
Change requests | [Request, impact, approval status]
Next milestone | [Name and forecast date]
Next report date | [Date]